## OKR
Employee Information
SBU/BD/Corp Funct： |  | Power | LOB/Div： | EVPS | Emp#：10027628 | JG： | Title：Senior FW Engineer | Name：Nilesh Mohanlal
No. | YR 2022 Target |  |  | Measure 檢核
|  |  |  | Dashboard 衡量指標 | Plans 行動計畫
[5 empty] | Item | Owner | Date | Progress | Actual
1 | Complete 11/22kW OBC combo PTT1 functional test by December 2022 |  |  | 1-1 11/22kW OBC combo firmware maturity | D1-1-1 Open loop simulation. D1-1-2 Close loop simulation D1-1-3 MBD creation for the OBC D1-1-4 MBD code generation | Nilesh | 2022-12-31 | 80% as of 15th July | On schedule as per plan.
2 | Process |  |  | Determine Working tools and processes that EVPS can get the economy of scale and implementation leadtime acceptable timeline. | D2-1-1 Selected Gitlab and Git as Tracking tool and Configuration Management tool. D2-1-2 To deploy in team. D2-1-3 Training and implementation. | Nilesh | 2022-07-31 | 100% completed as per plan | Deployed across various teams
3 | FSM |  |  | Determine process following FSM process and documentation can follow up accordingly. | D3-1-1: Process (RM, CM, etc.) according to FSM | Nilesh | 2022-07-31 | 100% completed as per plan | On going, actively supporting team on FSM topics
4 | Career Develoment |  |  | C/C++ Coding, Matlab simulink, Source code management, unit/functional test of code, Requirement and design mangement for the project. CI/CD and DevOps. | Explore areas in which can support team to aceive higher productivity | Nilesh | 2022-12-31 | 70% completed as per plan | Continous improvement topics on going.
5
6
7
8
9
10
OKR Scoring
Capability Matrix | [7 empty] | Target | Actual
CM Scoring | [8 empty] | 0
Total | [7 empty] | 0 | 0
註：績效評核之最終結果，另應參酌受評人核心職能表現進行綜合評斷。 Note: The final result of the performance appraisal shall also be comprehensively judged with reference to the performance of the assessee's core functions.
[6 empty] | Performance | PL1 PL2 PL3+ PL3 PL3- PL4 PL5
[6 empty] | Rating | □ □ □ □ □ □ □
Perf. Commitment: |  | Nilesh
|  | Prepared |  | Approved
Perf. Appraisal: |  | /
|  | Prepared |  | Approved

## Capability Matrix G8 to G14
Employee Information
SBU/BD/Corp Funct： |  | Power | LOB/Div： | EVPS | Emp#：10027628 | JG： | Title：Senior FW Engineer | Name：Nilesh Mohanlal
Capability Matrix (G8 to G14) | 2021 Actual | 2022 Target | WGT % | Need Improvement | Average | Met Expectation | Above Expectation | Excellence | 2022 Self assessment | HOD Assessment | HOD X WGT% Weight
Communication |  | 70 | 4.6% | 50 | 60 | 70 | 80 | 90 | 100 |  | 0
Teamworking |  | 70 | 4.6% | 50 | 60 | 70 | 80 | 90 | 100 |  | 0
Organizational Ability |  | 70 | 4.6% | 50 | 60 | 70 | 80 | 90 | 100 |  | 0
Leadership |  | 70 | 1.55% | 50 | 60 | 70 | 80 | 90 | 100 |  | 0
Technical Knowledge |  | 70 | 1.55% | 50 | 60 | 70 | 80 | 90 | 100 |  | 0
Decision Making |  | 70 | 1.55% | 50 | 60 | 70 | 80 | 90 | 100 |  | 0
Analytical Skills |  | 70 | 1.55% | 50 | 60 | 70 | 80 | 90 | 100 |  | 0
Total |  |  | 20% | 10% | 12% | 14% | 16% | 18% |  |  | 0